## Alpha Results Summary
Project Name |  | Chomp Sci Chatbot |  |  |  |  | Team Voltaic Sparrow
Prepared By |  | Robert Caplin
Date of Creation |  | 2023-03-22
Date of Review
Manual Functional Tests
| Item Number | Location | Traceability | Test Case ID | Date | Configuration | Tester | Comments | Status | Result
| 1 | ./functionalTests/VS00001_testCase_christopher.docx | R1 | VS00001 | 2023-03-20 | Chrome Version 111.0.5563.65 (Official Build) (64-bit) browser on Desktop Windows 10. | Christopher Schmidt | Pass. The chatbot properly follows the outcome of each test case on both Chrome. If you follow the steps described exactly, they will give you the outcome correctly. One issue when you don’t follow the steps exactly: If you use ‘Enter’ rather than clicking the ‘send’ button manually, there will be a white space in the text box that you need to clear. Although, this doesn’t significantly interfere with any functionality. | completed | PASS
| 2 | ./functionalTests/VS00001_testCase_christopher.docx | R1 | VS00001 | 2023-03-20 | Chrome version 111.0.5563.57 browser on Mobile (Android Samsung Galaxy S21+) | Christopher Schmidt | Pass. Although there are some marginal errors (such as spacing on the button), it does not affect functionality and the goals of the test. | completed | PASS
| 3 | ./functionalTests/VS00002_testCase_christopher.docx | R2 | VS00002 | 2023-03-20 | Chrome Version 111.0.5563.65 (Official Build) (64-bit) browser on Desktop Windows 10. | Christopher Schmidt | Fail. The chatbot fails on step 6 when given the directions to ask about “Computer Engineering” and “IT” using the provided phrases. This is likely a conflict with the Computer Science Topics intent, as it uses similar phrasing to the questions and provides the fallback answer of “I’m not well-trained on [entity].” | completed | FAIL
| 4 | ./functionalTests/VS00002_testCase_christopher.docx | R4 | VS00004 | 2023-03-20 | Chrome Version 111.0.5563.65 (Official Build) (64-bit) browser on Desktop Windows 10. | Christopher Schmidt | Pass. The bot properly responds with all of the expected answers, with the only issue being having to scroll to the top of two of the answers due to message length. | completed | PASS
Unit/ Component Tests
| Item Number | Location | Traceability | Test Case ID | Date | Configuration | Tester | Comments | Status | Result
| 5 | ./rasaTests/results | R2, R3, R4, R5, R6, R7 | VSR_01 | 2023-03-22 | N/A. Tests run within docker container on demand. | Robert Caplin | Fail. There are issues with intent recognition, entity extraction, and failing test stories. See analysis and test output in results folder. | completed | FAIL
| 6 | N/A, Simple Pass/Fail | R1, R2, R7 | VSUI_01 | 2023-03-22 | N/A. Tests run within docker container during build. | Robert Caplin | Pass. The tests are run during the build process and prevent it from completing if they do not pass. Build successful. | completed | PASS
| 7 | N/A, Simple Pass/Fail | R3 | VSDB_01 | 2023-03-23 | Windows 10 x64, Node v.18.14.2 (LTS) | Robert Caplin | Pass. The script and test queries completed successfully. | completed | PASS
SonarCloud Scan
| Item Number | Location | Traceability | Test Case ID | Date | Configuration | Tester | Comments | Status | Result
| 8 | Scan Results publicly available at: https://sonarcloud.io/summary/overall?id=rocaplin_VoltaicSparrow | N/A | N/A | 2023-03-20 | Scan against main branch of repo. | Robert Caplin | The scan identified 9 bugs, 0 vulnerabilities, 54 code smells, 8 security hotspots, and 3.1% duplications in the code base. It is important to note that results must be reviewed to assess their meaning. In general I don't think the categories are always correct but I think the results are useful. We will review the results and use them to improve what we have worked on. | completed | N/A

## Requirements Tested
Requirement | Description
R1 | The chatbot should be available to anyone with a modern browser.
R2 | The chatbot should provide a high-level view of Computer Science via a natural language interface.
R3 | Prospective students interested in Computer Science should be able to learn about related topics, courses, and careers.
R4 | Prospective students should be able to learn about the university experience.
R5 | Prospective studendts should be able to learn about the broad scope of topics that fall within Computer Science.
R6 | The chatbot should attempt to steer off-topic conversations to in-scope subjects.
R7 | The chatbot should link users to official UF webpages when appropriate.