## Alpha Results Summary
Project Name |  | Chomp Sci Chatbot |  |  |  |  | Team Voltaic Sparrow
Prepared By |  | Robert Caplin
Date of Creation |  | 2023-04-17
Date of Review |  | 2023-04-18
Manual Functional Tests
| Item Number | Location | Traceability | Test Case ID | Date | Configuration | Tester | Comments | Status | Result | Notes
| 1 | ./functionalTests/VS00001_testCase_PASS.docx | R1 | VS00001 | 2023-04-17 | Microsoft Edge Version 112.0.1722.48 (Official build) (64-bit) browser on Laptop Windows 11 | Katriana O’Hara | Pass. One issue noted is that the previous conversation does not get cleared when the user closes the chat window and reopens it. Aside from that, the bot successfully functions as described. | completed | PASS
| 2 | ./functionalTests/VS00001_testCase_PASS.docx | R1 | VS00001 | 2023-04-17 | Safari Version 16 browser on Mobile (iPhone 13 Pro Max) | Katriana O’Hara | Pass. Having the same issue as on Windows in which the previous conversation does not get cleared when the chat window is closed and reopened. Aside from that, the bot successfully functions as described. | completed | PASS | NOTE: The persistant chat-log was added to support the socket.io client requesting an initial message from Rasa on connection. I simply overlooked updating this step in the test case. - Bob
| 3 | ./functionalTests/VS00002_PASS.docx | R2 | VS00002 | 2023-04-17 | Microsoft Edge Version 112.0.1722.48 (Official build) (64-bit) browser on Laptop Windows 11 | Katriana O'Hara | Pass. Everything functions as expected. | completed | PASS
| 4 | ./functionalTests/VS00003_testCase_FAIL.docx | R3, R5 | VS00003 | 2023-04-17 | Microsoft Edge Version 112.0.1722.48 (Official build) (64-bit) browser on Laptop Windows 11 | Katriana O’Hara | Fail. Some of the course buttons do not have the course codes formatted properly so the lookup in the database fails. Duplication steps: 1. What's an algorithm? 2. Click "Classes?" 3. Click "COP3530". -> Course codes are supposed to be formated as "COP 3530". Some of the associated courses in compsci-topicsdata.csv are formatted incorrectly. | completed | FAIL | NOTE: This fix does not affect the model and as a result should be low risk.
| 5 | ./functionalTests/VS00004_testCase_PASS.docx | R4 | VS00004 | 2023-04-17 | Chrome Version 111.0.5563.65 (Official Build) (64-bit) browser on Desktop Windows 10. | Christopher Schmidt | Pass. The bot properly responds with all of the expected answers. The only difference being that there are additional outputs of follow-up questions or buttons, but these do not prevent the bot from fulfilling its role. | completed | PASS
| 6 | ./functionalTests/VS00006_testCase_PASS.docx | R6 | VS00006 | 2023-04-17 | Chrome Version 111.0.5563.65 (Official Build) (64-bit) browser on Desktop Windows 10. | Christopher Schmidt | Pass. The bot properly steers the user from off-topic conversation and suggests known conversation topics. | completed | PASS
| 7 | ./functionalTests/VS00007_testCase_PASS.docx | R7 | VS00007 | 2023-04-17 | Chrome Version 111.0.5563.65 (Official Build) (64-bit) browser on Desktop Windows 10. | Christopher Schmidt | Pass. The chatbot links to pages when appropriate, and the links function properly as well. | completed | PASS
Unit/ Component Tests
| Item Number | Location | Traceability | Test Case ID | Date | Configuration | Tester | Comments | Status | Result
| 8 | ./rasaTests/results | R2, R3, R4, R5, R6, R7 | VSR_01 | 2023-04-17 | N/A. Tests run within docker container on demand. Note: Tests were completed using the "chomp_mvp.tar.gz" model. Rasa uses a caching system to reduce training time, previously trained models serve as the base of newly trained models. We have found that cached models | Robert Caplin | Fail. - 61 / 71 test stories pass during unit testing - 9 of the 10 failing test stories work properly when manually tested Overall, 70 / 71 unit tests pass. The failing unit test requires modification of training data. While this fix is easy to apply... it reduces the overall performance of the model. This would require working other parts of the training data after applying the fix to bring overall performance back up to where it currently is. | completed | FAIL | NOTE: This fix would require us to modify the model which can have unpredictible results. In this case, it reduces the overall performance of the model and so is a high risk change that would require additional changes afterwards.
| 9 | N/A, Simple Pass/Fail | R1, R2, R7 | VSUI_01 | 2023-04-17 | N/A. Tests run within docker container during build. | Robert Caplin | Pass. The tests run during the build process and prevent it from completing if they do not pass. Build successful. | completed | PASS
| 10 | N/A, Simple Pass/Fail | R3 | VSDB_01 | 2023-04-17 | Windows 10 x64, Node v.18.14.2 (LTS) | Robert Caplin | Pass. The script and test queries completed successfully. | completed | PASS
SonarCloud Scan
| Item Number | Location | Traceability | Test Case ID | Date | Configuration | Tester | Comments | Status | Result
| 11 | Scan Results publicly available at: https://sonarcloud.io/summary/overall?id=rocaplin_VoltaicSparrow | N/A | N/A | 2023-04-17 | Scan against main branch of repo. | Robert Caplin | The scan identified 1 bug, 0 vulnerabilities, 21 code smells, 8 security hotspots, and 0.0% duplications in the code base. It is important to note that results must be reviewed to assess their meaning. In general I don't think the categories are always correct but I think the results are useful. We will review the results and use them to improve what we have worked on. | completed | N/A

## Requirements Tested
Requirement | Description
R1 | The chatbot should be available to anyone with a modern browser.
R2 | The chatbot should provide a high-level view of Computer Science via a natural language interface.
R3 | Prospective students interested in Computer Science should be able to learn about related topics, courses, and careers.
R4 | Prospective students should be able to learn about the university experience.
R5 | Prospective studendts should be able to learn about the broad scope of topics that fall within Computer Science.
R6 | The chatbot should attempt to steer off-topic conversations to in-scope subjects.
R7 | The chatbot should link users to official UF webpages when appropriate.